## User stories group ...
|  | iteration 1 |  |  | iteration 2 |  |  | iteration 3 |  |  | iteration 4
nr | title | PPs | priority | status | PPs | priority | status | PPs | priority | status | PPs | priority | status
1 | Create Players | 2 | M | open | 1 | M | closed
2 | Assign Money/Budget | 1 | S | closed
3 | Show the board/gui |  | M | cancelled
4 | Select player | 2 | S | open | 2 | M | closed
5 | Roll the dice and move to correct tile | 4 | M | cancelled
6 | Draw (pre-created) Cards | 3 | C | cancelled
7 | Create Sequential turn order | 2 | M | open | 5 | M | closed
8 | Finishing the game | 2 | W | open | 2 | S | cancelled
9 | Roll the dice, move to the correct tile, and get a card |  |  |  | 4 | M | closed
10 | Execute the card |  |  |  | 1 | M | closed
11 | Show the interactive board/UI |  |  |  | 10 | M | closed
12 | Have a full deck of cards | [6 empty] | 4 | M | open | 2 | M | closed
13 | Give cards differing functionalities so that they warrant subclass use | [6 empty] | 6 | M | open | 2 | M | closed
14 | Scaling the GUI | [6 empty] | 1 | S | closed
15 | Add Salary Tiles | [6 empty] | 3 | M | cancelled
16 | Handle negative money | [6 empty] | 2 | C | cancelled
17 | Branching tiles on the board | [6 empty] | 8 | S | closed
18 | Being able to buy bonusses with money | [6 empty] | 5 | C | cancelled
19 | Add Background to board panel | [6 empty] | 2 | S | closed
20 | Get income | [9 empty] | 2 | M | closed
21 | Have an extended path | [9 empty] | 4 | M | closed
22 | Player names and countries are chosen and displayed | [9 empty] | 2 | S | closed
23 | Finishing the game | [9 empty] | 6 | M | closed
24 | Buying victory points | [9 empty] | 5 | M | closed
25 | Disallow negative money | [9 empty] | 2 | M | closed